## Project 1
CyberX Sprint Logs
Completed by: |  |  | Victoria Hektor
Deadline: |  |  | 05/05/2023 12 noon
Sprint Logs
% done | Sprint No. | Instruction | Date | Due By | Completed? | Notes
100% | 1 | Frontend | January 13th | February 13th | Y | This month focus on as a minimum creating a working interface demo.
100% | 2 | Backend | February 14th | March 15th | N | I can't get the backend working, I think I am trying to do too much at once but I can't seem to figure a way around this.
100% | 3 | Backend | March 16th | April 16th | N | I am still having the same issues, I planned a set of small tasks to focus on each individual functionality, this worked, although I haven't completed all of the functionality, I am able to demo some of the backend functionality I wanted to.
100% | 4 | Finishing up | April 16th | May 5th | Y/N | Partially completed and pleased I actually got some of the backend to work!
Sprint Logs - Functionality
% done | Sprint No. | Function | Date | Due By | Completed? | Notes
100% | 1 | Login/Logout | January 13th | February 13th | Y | I have a working version, but not all together with the whole project.
100% | 2 | Database | February 14th | March 15th | Y | I have a working database 'cyberx' with 2 tables, room to add more if time.
100% | 3 | Dashboard | March 16th | April 16th | Y/N | I have managed to get a working admin dashboard that adds, views and updates users.
100% | 4 | Finishing up | April 16th | May 5th | Y/N | For this I am trying to bring everything together to work as one whole application as opposed to just individual working functions.

## Project 2
CyberX Sprint Logs
To be completed by: |  | Name
Deadline: |  | Date
Project 2
% done | Phase | Due by | Notes
0% | Planning
0% | Preparation
0% | Task a
0% | Task b
0% | Task c
0% | Task d
0% | Paperwork
0% | Hand-off
0% | Follow-up

## Project 3
CyberX Sprint Logs
To be completed by: |  | Name
Deadline: |  | Date
Project 3
% done | Phase | Due by | Notes
0% | Planning
0% | Preparation
0% | Task a
0% | Task b
0% | Task c
0% | Task d
0% | Paperwork
0% | Hand-off
0% | Follow-up