## FrontEnd
CyberX Testing
To be completed by: |  | Victoria Hektor
Deadline: |  | 2023-05-05
Functionality Testing (HTML)
% done | Test Name | Actual Test | Expected Result | Actual Result | Working? | Notes
100% | Homepage (HP) – Links & buttons, View & Navigation | Clicking all Buttons on the home Page, ensuring the view is as expected | Navigates to expected page and the view is as expected | Some didn't navigate which highlighted some name link issues | No | Went through and changed the names to the right ones, Although I am still not happy about my logo placement and size or the header
100% | Learning Platform (LP) - Links & buttons, View & Navigation | Clicking all Buttons on the LP, ensuring the view is as expected | Navigates to expected page and the view is as expected | Some didn't navigate which highlighted some name link issues | No | Went through and changed the names to the right ones, Although I am still not happy about my logo placement and size or the header
100% | Resources Page (R.) - Links & buttons, View & Navigation (Include subsequent buttons/links (Resources) | Clicking all Buttons on the R Page, ensuring the view is as expected | Navigates to expected page and the view is as expected | Some didn't navigate which highlighted some name link issues | No | Went through and changed the names to the right ones, Although I am still not happy about my logo placement and size or the header
100% | Login/Logout/Register Page (LL & R) - Links, buttons and view | Clicking all Buttons on the LL & R Page, ensuring the view is as expected | Navigates to expected page and the view is as expected | Some didn't navigate which highlighted some name link issues | No | Went through and changed the names to the right ones, Although I am still not happy about my logo placement and size or the header
100% | Members Area (MA) - Links & buttons, View & Navigation | Clicking all Buttons on the MA Page, ensuring the view is as expected | Navigates to expected page and the view is as expected | Some didn't navigate which highlighted some name link issues | No | Went through and changed the names to the right ones, Although I am still not happy about my logo placement and size or the header
100% | Course Pages (C) - Links & buttons, View & Navigation (x4 pages) | Clicking all Buttons on the C Page, ensuring the view is as expected | Navigates to expected page and the view is as expected | Some didn't navigate which highlighted some name link issues | No | Went through and changed the names to the right ones, Although I am still not happy about my logo placement and size or the header
100% | About Us Page (AU) - Links & buttons, View & Navigation | Clicking all Buttons on the AU Page, ensuring the view is as expected | Navigates to expected page and the view is as expected | Some didn't navigate which highlighted some name link issues | No | Went through and changed the names to the right ones, Although I am still not happy about my logo placement and size or the header
100% | Contact Us Page (CU) - Links & buttons, View & Navigation | Clicking all Buttons on the CU Page, ensuring the view is as expected | Navigates to expected page and the view is as expected | Some didn't navigate which highlighted some name link issues | No | Went through and changed the names to the right ones, Although I am still not happy about my logo placement and size or the header
100% | Follow-up notes: | All had the same issue, went through the application again and retested, results below.
Functionality Testing (HTML) - Retest
% done | Test Name | Actual Test | Expected Result | Actual Result | Working? | Notes
100% | Homepage (HP) – Links & buttons, View & Navigation | Clicking all Buttons on the home Page, ensuring the view is as expected | Navigates to expected page and the view is as expected | Navigated Correctly | Yes | All Navigates Correctly.
100% | Learning Platform (LP) - Links & buttons, View & Navigation | Clicking all Buttons on the LP, ensuring the view is as expected | Navigates to expected page and the view is as expected | Navigated Correctly | Yes | All Navigates Correctly.
100% | Resources Page (R.) - Links & buttons, View & Navigation (Include subsequent buttons/links (Resources) | Clicking all Buttons on the R Page, ensuring the view is as expected | Navigates to expected page and the view is as expected | Navigated Correctly | Yes | All Navigates Correctly.
100% | Login/Logout/Register Page (LL & R) - Links, buttons and view | Clicking all Buttons on the LL & R Page, ensuring the view is as expected | Navigates to expected page and the view is as expected | Navigated Correctly | Yes | All Navigates Correctly.
100% | Members Area (MA) - Links & buttons, View & Navigation | Clicking all Buttons on the MA Page, ensuring the view is as expected | Navigates to expected page and the view is as expected | Navigated Correctly | Yes | All Navigates Correctly.
100% | Course Pages (C) - Links & buttons, View & Navigation (x4 pages) | Clicking all Buttons on the C Page, ensuring the view is as expected | Navigates to expected page and the view is as expected | Navigated Correctly | Yes | All Navigates Correctly.
100% | About Us Page (AU) - Links & buttons, View & Navigation | Clicking all Buttons on the AU Page, ensuring the view is as expected | Navigates to expected page and the view is as expected | Navigated Correctly | Yes | All Navigates Correctly.
100% | Contact Us Page (CU) - Links & buttons, View & Navigation | Clicking all Buttons on the CU Page, ensuring the view is as expected | Navigates to expected page and the view is as expected | Navigated Correctly | Yes | All Navigates Correctly.
100% | Follow-up notes: | I am still unhappy regarding the logo placement and size and will work on this.

## Processes
CyberX Testing
To be completed by: |  | Victoria Hektor
Deadline: |  | 2023-05-05
Processes Testing (Login/Logout etc)
% done | Test Name | Actual Test | Expected Result | Actual Result | Working? | Notes
100% | Register | Click register, Add in Details | Registers user and shows a success message | I managed to register an admin user but then it stopped working, I am not sure why. | No | When I change things in the code it doesn't work. I can add users in PHPMyAdmin no problem
100% | Login | Enter in existing details and click login | Successful login, shows user dashboard | It navigates to the PHP file for the login Query. (Blank) | No | I think this needs to change but not sure what, will look at it again and retest
100% | Logout | Click logout button | Shows success message for logging out | I have not managed to test this as of yet due to an error logging in/registering. | No | unable to test yet
100% | Learning Platform | Navigate the the learning platform page (Do as a visitor and as a user) | Shows the correct format for either a visitor or a user | I can navigate here as a visitor but not a user yet as my backend is not working correctly. | No | Unable to test yet
100% | User Dashboard | Login as a user and click on Dashboard | Correctly shows a user profile and dashboard | As the backend isn't working yet, I cannot navigate here as a logged in user. | No | I have set up a demo whereby it shows the user journey to logging in via HTML code.
100% | SuperUser Dashboard (Admin) | Login as the super user and click on dashboard | Correctly shows admin dashboard with admin privileges | As the backend isn't working yet, I cannot navigate here as a logged in user. | No | I have set up a demo whereby it shows the user journey to logging in via HTML code.
Processes Testing (Login/Logout etc) - Retests
% done | Test Name | Actual Test | Expected Result | Actual Result | Working? | Notes
100% | Register | Click register, Add in Details | Registers user and shows a success message
100% | Login | Enter in existing details and click login | Successful login, shows user dashboard
100% | Logout | Click logout button | Shows success message for logging out
100% | Learning Platform | Navigate the the learning platform page (Do as a visitor and as a user) | Shows the correct format for either a visitor or a user
100% | User Dashboard | Login as a user and click on Dashboard | Correctly shows a user profile and dashboard
100% | SuperUser Dashboard (Admin) | Login as the super user and click on dashboard | Correctly shows admin dashboard with admin privileges
Processes Testing (Admin Dashboard etc)
% done | Test Name | Actual Test | Expected Result | Actual Result | Working? | Notes
100% | Add User | add a user via the dashboard | Adds new user | Correctly adds a user | Y | Checked via interface and via PHPMyAdmin
100% | Delete User | Delete selected user | Deletes User | Asks if I am sure, press ok, then deletes | Y | Checked via interface and via PHPMyAdmin
100% | Edit User | Edit user details | Correctly changes details | It doesn't display anything | N | Worked on trying to debug but couldn't figure out.
100% | Add Course | Add a course via the admin dashboard | Adds a course | Correctly adds course |  | Checked via interface and via PHPMyAdmin
100% | Edit Course | Edit a course via the admin dashboard | Correctly edits the course details of choice | It doesn't display anything | N | Worked on trying to debug but couldn't figure out.
100% | Delete Course | Delete a course via the admin dashboard | Deletes chosen course | Gives correct interface but doesn't delete | N | I have tried separating this function and used javascript in the html code.
| View All Courses | Click 'view all courses' | correctly shows all courses | correctly shows all courses | Y | No issues
100% | View All Users | Click 'view all users' | Correctly shows all users | Correctly shows all users | Y | No issues
Processes Testing (Admin Dashboard retest)
% done | Test Name | Actual Test | Expected Result | Actual Result | Working? | Notes
100% | Edit User | Edit user details | Correctly changes details | It doesn't display anything | N | Worked on trying to debug but couldn't figure out.
100% | Edit Course | Edit a course via the admin dashboard | Correctly edits the course details of choice | It doesn't display anything | N | Worked on trying to debug but couldn't figure out.
100% | Delete Course | Delete a course via the admin dashboard | Deletes chosen course | Gives correct interface but doesn't delete | N | I have tried separating this function and used javascript in the html code.

## BackEnd
CyberX Testing
To be completed by: |  | Victoria Hektor
Deadline: |  | 2023-05-05
BackEnd Testing (PHP, MySQL)
% done | Test Name | Actual Test | Expected Result | Actual Result | Working? | Notes
100% | Create Tables | Create a DB for users and relevant data that needs storing | Success on creating table via automated PHP/SQL script | I am able to create the database in PHPMyAdmin but not on the HTML interface I created | No | Able to do in PHPMyAdmin but not the interface I have created, will try and get working in time for viva.
100% | User Validation | Checks existing DB for user info, then adds new user or logs existing user in. Validates PW, and Username. | Success message for either new user creation or existing user login. Successful error handling for incorrect login/register | I am able to create the user as an admin in PHPMyAdmin but not on the HTML interface I created | No | Able to do in PHPMyAdmin but not the interface I have created, will try and get working in time for viva.
100% | Super user validation | Test to check validation, privileges and access | Successful error handling with incorrect login, checks PW, checks privileges and | I am able to be an admin in PHPMyAdmin but not on the HTML interface I created via logging in | No | Able to do in PHPMyAdmin but not the interface I have created, will try and get working in time for viva.
100% | Database Management | Test to ensure DB can be managed by super user, adding or removing users. | Success on adding and removing users. | I am able to create the database in PHPMyAdmin but not on the HTML interface I created | No | Able to do in PHPMyAdmin but not the interface I have created, will try and get working in time for viva.
BackEnd Testing (PHP, MySQL) - Retest
% done | Test Name | Actual Test | Expected Result | Actual Result | Working? | Notes
100% | Create Tables | Create a DB for users and relevant data that needs storing | Success on creating table via automated PHP/SQL script
100% | User Validation | Checks existing DB for user info, then adds new user or logs existing user in. Validates PW, and Username. | Success message for either new user creation or existing user login. Successful error handling for incorrect login/register
100% | Super user validation | Test to check validation, privileges and access | Successful error handling with incorrect login, checks PW, checks privileges and
100% | Database Management | Test to ensure DB can be managed by super user, adding or removing users. | Success on adding and removing users.

## Code
CyberX Testing
To be completed by: |  | Victoria Hektor
Deadline: |  | 2023-05-05
Code Testing (PHP, HTML)
% done | Test Name | Actual Test | Expected Result | Actual Result | Working? | Notes
100% | Code Testing | PHP Unit | No bugs
100% | PHP Syntax | PHP Code Checker | No code errors, syntax correct
100% | PHP Indentation | PHP Code Sniffer - Can be done within PHP Storm and automated | Code styling correct | Some indentation issues | No | Will work through to put the correct indentations in then retest
100% | PHP Coding Standards | PHP Code Sniffer - | Code standards correct
100% | HTML Validation | W3 Markup (Online) - Copy & Paste into browser | No HTML Errors | Some errors and wrong indentations | No | Will go through and fix them then retest
100% | Var Dump (For Functions) | Test to check what is happing with any functions, will test all. | No issues and functions working as expected
Code Testing (PHP, HTML) - Retest
% done | Test Name | Actual Test | Expected Result | Actual Result | Working? | Notes
100% | Code Testing | PHP Unit | No bugs
100% | PHP Syntax | PHP Code Checker | No code errors, syntax correct
100% | PHP Indentation | PHP Code Sniffer - Can be done within PHP Storm and automated | Code styling correct | Some indentation issues | No | Will work through to put the correct indentations in then retest
100% | PHP Coding Standards | PHP Code Sniffer - | Code standards correct
100% | HTML Validation | W3 Markup (Online) - Copy & Paste into browser | No HTML Errors | Some errors and wrong indentations | No | Will go through and fix them then retest
100% | Var Dump (For Functions) | Test to check what is happing with any functions, will test all. | No issues and functions working as expected